## Raw (hidden)
Goal
1. Account Creation Test | Check for smoothness, deposit and success rate, user feedback
2. Employer Job Posting Test | Check for smoothness, success rate, confidence, user feedback
3. Jobseeker Application Test | Check for smoothness, navigation, completion and user feedback
4. Acceptance and Completion Test | Check for both user feedback on what they think about the method
5. Multiple application test | Check for user feedback
6. Service Delivery Test | Check for user feedback and map usability
7. Rental posting test | Check for user feedback
8. Rental application test | Check for user feedback
Core Testing Goal
Can users understand the app quickly? | Yes, but there are areas that needs to be updated for user convenience and better experience
Can they complete a service booking/job posting easily? | Yes, but the code copying and sending is a hassle. Jobseeker also thought of the fact that he needs to wait for the code before receiving his pay, what if he's in a hurry
What confuses or frustrates them? | Some terminologies and functionalities.
Would they actually use it in real life? | Yes, very positive. The app has a lot of use case as per the testers.
What prevents trust and transactions? | Use of foul words are not blocked, some enhancement in the flow also needs to be updated.
PART 1 — First Impression Questions
(Ask before explaining too much)
1. “What do you think this app is for?” | Aesthetic, nice UI
This tells you whether your app positioning is clear.
2. “If you discovered this app on Facebook or TikTok, would you download it? Why or why not?”
This reveals perceived value instantly.
UI is nice
3. “What is the first thing that caught your attention?”
Helps identify strongest UI/value elements.
4. “Was anything confusing immediately?” | Get things Done, Earn Money a bit confusing
Critical for onboarding. | Company Name Confusing
Picture Requirement should be optional but enhances chances of success rate if provided
Password checking is not available
PART 2 — Navigation & Ease of Use
(Have them perform tasks)
Ask them to:
Add funds | Add funds manual input errors, max amount not specified, add funds fails to load when pop ups are blocked,
Find a service | Illegal Postings immediate checking not available, Remote or Personal option should be automatic based on job category, Location not 100%accurate and cannot be pinned easily, Main Job Category not shown in the posting,
Book someone
Post a job/service
Message a provider | Message button confusing, should be easily found
Check profile/rating/payment flow | Job progress in profile confusing or cannot be found immediately, accept job for jobseeker confusing, code copy and paste not available both ends,
Rating and feedback ok, space function not functioning always
Then ask: | Accept offer confusing, better to have direct option upon job availability
Job proof of completion not seen immediately or historically
5. “What part felt hardest or slowest?” | Usuable is great once a job is completed.
This identifies UX friction. | CP Map view to check for available jobs not functioning properly
Job posted and applied from multiple users error on who was accepted was not visible and when its in the ongoing jobs, all applicants are still there and not specific to the accepted person only
6. “Was there any moment you didn’t know what to do next?” | View for code should be more efficient and convenient, copy and send to jobseeker function is better.
Extremely important. | There was an instance where jobseekers where still able to apply even one jobseeker has been accepted already
7. “Did you feel overwhelmed by anything?” | For rental deposit, put percent instead of manual input
Too many buttons/features kill conversion. | Vehicle model info not visible
8. “How many taps do you think were unnecessary?”
You’ll discover inefficient flows.
PART 3 — Trust & Safety Questions
This is HUGE for marketplace apps.
9. “Would you trust hiring someone from this app?”
If no, ask WHY specifically.
10. “What would make you feel safer using this app?”
Examples:
Verified IDs
Ratings
Escrow
Reviews
Real photos
Background checks
This feedback is gold.
11. “Would you trust receiving payment through this app?”
Critical for providers/jobseekers.
PART 4 — Real-World Usage Questions
12. “What service would you personally use first here?”
Helps identify strongest categories.
13. “What type of people do you think would use this app most?”
Great for marketing direction.
14. “Would you actually post or accept jobs here?”
Ask them to rate confidence from 1–10.
15. “What would stop you from using this regularly?”
One of the most important questions.
PART 5 — Competitive & Value Questions
16. “What apps does this remind you of?” | Linked In
You’ll learn your market positioning.
17. “Why would someone choose this over Facebook posts or referrals?”
This reveals whether your value proposition is strong enough.
18. “What feature feels most valuable?”
Prioritize development around this.
19. “What feature feels unnecessary or weak?”
Helps avoid feature bloat.
PART 6 — Emotional & Retention Questions
20. “After trying it, how likely are you to recommend this app to a friend?”
(Simple NPS-style question)
21. “If this app disappeared tomorrow, would you care?”
This reveals actual product-market pull.
22. “What is ONE thing you would improve immediately?” | Code Transfer
Probably your highest ROI insight. | Proof
Funds Limit
The MOST Important Thing During Testing
Do NOT over-explain the app.
The more you explain:
the less real the test becomes
the more biased the feedback gets
Instead:
Observe where they hesitate
Watch where they tap
Notice where they get confused
Pay attention to facial reactions
Those are often more valuable than their verbal answers.
Best Structure for Your 10 Testers
Suggested Flow (15–20 mins each)
Step 1 — Silent Observation (5 mins)
Give them tasks without helping.
Example:
“Find someone to clean a house.”
“Post a plumbing service.”
“Send a message to a provider.”
Observe everything.
Step 2 — Ask Essential Questions (10 mins)
Focus on:
confusion
trust
usability
real-world likelihood of use
Step 3 — Final Rating (1 min)
Ask:
Ease of use: /10
Trust level: /10
Likelihood to use: /10
Likelihood to recommend: /10
This gives measurable feedback.
Biggest Mistake Founders Make in User Testing
They defend the app.
Never defend.
Never justify.
If users are confused, that confusion is the product feedback.
Even if you think they’re “using it wrong.”
Bonus: The 5 Highest-Value Questions Overall
If you only ask 5, ask these:
“What do you think this app does?”
“Was there any moment you felt confused?”
“Would you trust using this app with real money/services?”
“What would stop you from using this regularly?”
“What is the ONE thing you would improve immediately?”

## Test Summary
Section | Summary | Key Findings | Recommended Focus
Overall Testing Conclusion | Testing results are highly promising. Users immediately saw practical value and said they would realistically use Terra.Ph for services, jobs, and rentals. | Core product concept is validated. Main friction points are payment flow, navigation clarity, trust controls, terminology confusion, map usability, and transaction visibility. | Simplify workflows, improve visibility of key actions, strengthen trust systems, and reduce unnecessary steps.
What Users Liked Most | Users responded positively to the app’s concept and design. | Clean UI, useful marketplace concept, strong service+rental combination, smooth experience after job completion, ratings system appreciated. | Preserve simplicity while refining flow consistency.
Biggest Pain Point: Payment Completion Flow | This was the most frustrating experience for testers. | Manual code copying and sending feels slow, inconvenient, and confusing. Workers dislike waiting for code release before payment. | Add copy/send code buttons, auto-fill verification, in-app verification popup, and direct “Release Payment” flow.
Navigation & Flow Confusion | Users generally understood the app but struggled with specific actions. | Accept Job button, Message button, job progress tracking, accepted applicant visibility, proof history, code access, company name field, wording clarity. | Make buttons larger, improve CTA visibility, simplify wording, improve dashboard hierarchy.
Job Application Logic Issues | Critical backend logic issue found. | Applicants remain visible after acceptance, users can still apply after hiring is closed, accepted worker not clearly shown. | Auto-close applications, disable further applications, highlight selected worker, move others to “Not Selected.”
Map & Location Problems | Location flow caused usability friction. | Pinning is difficult, GPS accuracy inconsistent, map loading weak. | Add drag-and-drop pin, searchable address, “Use Current Location,” better GPS refresh.
Trust & Safety Weaknesses | Trust is not yet strong enough for real-money adoption. | Foul words are not blocked, illegal postings not detected, weak moderation visibility. | Add profanity filter, keyword detection, report system, verified IDs, reliability badges.
Rental Module Feedback | Module is promising but needs polish. | Deposit setup confusing, vehicle details weak, no clear completion after rental expiry. | Add percentage-based deposit selector, improve vehicle display, automate rental completion.
Add Funds Experience | Funding process needs reliability improvements. | Manual input errors, limits unclear, popup dependency causes failures, weak loading feedback. | Show min/max limits, improve validation, remove popup dependency, stronger loading feedback.
Profile & Progress Visibility | Users struggled to track job lifecycle clearly. | Hard to locate active jobs, accepted jobs, proof history, payment waiting status. | Improve dashboard segmentation for both employers and jobseekers.
Immediate Priority Improvements (Tier 1) | Critical issues directly affecting trust and usability. | Payment flow, application logic, button visibility, profanity filtering, job visibility, map reliability. | Address immediately in next sprint.
Secondary Improvements (Tier 2) | Important but not blocking launch quality. | Better wording, rental refinements, add-funds polish, vehicle detail improvements, proof visibility. | Schedule after Tier 1 completion.
Strongest Product Validation Signal | Product-market interest is clearly present. | Users already see utility, convenience, and monetization potential. | Focus on friction reduction rather than concept changes.
UX Principle Moving Forward | Every screen should feel obvious within seconds. | Users should instantly know what is happening, what to do next, and what action matters most. | Reduce hesitation points through better visual guidance.
Recommended Next Testing Round | Test again after fixes are implemented. | Measure task completion time, taps, confusion points, trust confidence, completion success rate. | Retest posting, applying, hiring, payment release, and rentals.
Final Product Assessment | Terra.Ph is beyond idea validation. | Strong concept validation, strong real-world relevance, positive emotional response, scalable marketplace potential. | Enter refinement and scalability stage with UX optimization focus.

## Action Taken
Priority | Module | Issue Found | User Feedback / Observation | Recommended Enhancement | Action Taken | Status
HIGH | Onboarding | Confusing tagline | “Get Things Done, Earn Money” was unclear | Simplify wording into clearer CTA such as “Hire Services” and “Find Jobs” |  | ☐
MEDIUM | Onboarding | Company Name field confusing | Users unsure what to input | Rename to “Business/Company Name (Optional)” Make the field visible only when needed |  | ☐
LOW | Onboarding | Picture requirement too strict | Users prefer optional upload | Make profile picture optional but recommend it for better success rate |  | ☐
HIGH | Account Creation | No password validation | Users unsure if password is valid/strong | Add password strength checker and validation hints or view password button for checking |  | ☐
HIGH | Wallet / Add Funds | Manual amount entry errors | Users entered incorrect values | Add preset amounts and better validation |  | ☐
HIGH | Wallet / Add Funds | No visible min/max limits | Users unaware of funding limits | Display minimum and maximum funding amount clearly, set max deposit to 50k per transaction |  | ☐
HIGH | Wallet / Add Funds | Popup blocking issue | Add funds page fails when popups are blocked | Remove popup dependency or add fallback flow |  | ☐
MEDIUM | Wallet / Add Funds | Loading feedback weak | Users unsure if process is loading | Add loading animation and processing status, add auto refresh function |  | ☐
HIGH | Services / Job Posting | Illegal postings not filtered | Harmful or prohibited jobs can be posted | Add prohibited keyword detection and moderation filter |  | ☐
HIGH | Services / Job Posting | Remote/Personal option confusing | Users unsure which to choose | Auto-detect based on selected category, only show option if under "Others" job category |  | ☐
HIGH | Services / Job Posting | Main job category not visible | Difficult to identify jobs quickly | Show main category prominently in listings |  | ☐
HIGH | Maps / Location | Location inaccurate | Users struggled with exact location | Improve GPS accuracy and refresh logic, Brgy should be searchable easily |  | ☐
HIGH | Maps / Location | Pinning location difficult | Users had trouble placing pin | Enhance drag-and-drop map pin feature |  | ☐
MEDIUM | Maps / Location | No quick location selection | Too many steps for location setup | Add “Use Current Location” button |  | ☐
HIGH | Messaging | Message button hard to find | Users struggled to contact providers | Make message more visible in job posting details |  | ☐
HIGH | Job Application Flow | Accept job flow confusing | Users unsure how to proceed after applying | Simplify acceptance flow and add clearer CTA buttons |  | ☐
VERY HIGH | Job Application Flow | Applicants still visible after acceptance | Causes confusion in ongoing jobs | Hide non-selected applicants after acceptance |  | ☐
VERY HIGH | Job Application Flow | Users can still apply after someone accepted | Causes duplicate applications | Auto-close applications once worker is accepted, should no longer be visible in the other applicants view |  | ☐
VERY HIGH | Job Application Flow | Accepted worker not highlighted | Users unsure who got selected | Clearly highlight accepted applicant |  | ☐
HIGH | Job Tracking | Ongoing jobs difficult to locate | Users cannot track active work easily | Improve dashboard visibility for active jobs |  | ☐
HIGH | Job Tracking | Proof of completion not visible historically | Users cannot review old proofs | Add completion history section |  | ☐
VERY HIGH | Payment / Completion | Manual code transfer inconvenient | Copying and sending code is a hassle | Add automatic in-app verification flow only to employer side when completing the job |  | ☐
VERY HIGH | Payment / Completion | No copy-paste convenience | Users manually type codes | Add “Copy Code” button |  | ☐
VERY HIGH | Payment / Completion | Sending code manually inefficient | Slows down transactions | Add “Send Code” button with one tap |  | ☐
HIGH | Payment / Completion | Workers worry about delayed payment | Users fear waiting too long | Add direct “Release Payment” option |  | ☐
MEDIUM | Payment / Completion | Verification flow not intuitive | Users unsure where to find codes | Improve visibility and placement of verification section |  | ☐
MEDIUM | Ratings & Feedback | Space bar issue in feedback | Input field bug observed | Fix text input and spacing issue |  | ☐
VERY HIGH | Trust & Safety | Foul words not blocked | Reduces professionalism and trust | Add profanity filter |  | ☐
MEDIUM | Rental Posting | Deposit setup confusing | Manual input difficult | Use percentage-based deposit selection |  | ☐
MEDIUM | Rental Posting | Vehicle model info weak | Users cannot identify vehicles properly | Improve vehicle details visibility, show vehicle model clearly |  | ☐
HIGH | Rental Completion | Rental completion unavailable after expiry | Users unsure how rentals end | Add automatic rental completion after time expiry or put manual return button |  | ☐
HIGH | Dashboard / UX | Too many hidden actions | Users hesitate during navigation | Surface primary actions more clearly |  | ☐
HIGH | Dashboard / UX | Important actions buried in menus | Slows down usability | Redesign action hierarchy and CTA placement |  | ☐
HIGH | Dashboard / UX | Users unsure of next step | Causes hesitation and dropoff | Add clearer progress/status indicators |  | ☐
OVERALL CHECKLIST
MEDIUM | General UX | Too many taps in some flows | Users want faster interactions | Reduce unnecessary steps and clicks |  | ☐
HIGH | General UX | CP map job browsing not functioning properly | Difficult to browse nearby jobs | Optimize map performance and filtering |  | ☐
HIGH | General UX | Users confused by current workflow | Flow not intuitive enough | Simplify user journey from posting to completion |  | ☐
HIGH | Overall Retention | Trust still developing | Users need more confidence for real transactions | Improve escrow, verification, and moderation systems |  | ☐
HIGH | Overall Product | Real-world usage validated | Users see strong practical value | Continue refining convenience and trust systems |  | ☐